## Sheet1
Typical schedule for a 4 day Assurance Review (NB: for longer reviews add additional days for interview)
Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
08:30 - 09:00 | RT prep time (optional) | RT prep time (optional) | RT prep time (optional) | RT prep time (optional) | Review Team Draft Report
09:00 - 10:00 | Interview with Perm Sec | Interview tbc | Interview tbc | Interview tbc
10:00 - 11:00 | Interview with CPDO | Interview tbc | Interview tbc | Interview tbc
11:00 - 12:00 | Meeting with Portfolio Director | Interview tbc | Interview tbc | Interview tbc
12:00 - 13:00 | Lunch | Lunch | Lunch | Lunch
13:00 - 14:00 | Interview tbc | Interview tbc | Interview tbc | Interview tbc
14:00 - 15:00 | Interview tbc | Interview tbc | Interview tbc | Interview tbc
15:00 - 16:00 | Interview tbc | Interview tbc | Interview tbc | Interview tbc | It is good practice to book some reading-time for your SRO & PD, to review the draft report immeditely prior to the final feedback meeting.
16:00 - 17:00 | Interview tbc | Interview tbc | Interview tbc | Interview tbc | Final Feedback Meeting with Portoflio Director/HOP
17:00 - 17:30 | RT prep for wash-up | RT prep for wash-up | RT prep for wash-up | RT prep for wash-up
17:30- 18:00 | Wash-up briefing with SRO | Wash-up briefing with Wash-up briefing with Portfolio Director | Wash-up briefing with Wash-up briefing with Portfolio Director
Notes: | Allow 1hr slots for interviews. This will allow 45mins for the interview, 10mins for RT to discuss and a 5min comfort break.
The maximum number of interview per day is 7 but 6 would be preferable.
Leave at least 30mins after final interview of the day and the Portfolio Director wash-up briefing. This will allow time for the RT to organise their feedback.
On the final day try and make the Feedback Meeting (FM) late in the day so the RT have enough time to complete the report.
The RT will try and deliver a draft report within an hour of the FM. If you can leave enough time for the Portoflio Director to read it through prior to the FM then that will make for a better session.