## Sheet1
Entity	Attribute ID	Attribute name	Definition	Format	Update frequency	Example	Related NOVA/Finance/HR data standard ID
Project features	GPD_1002_S_001	Project / Programme ID	Unique alphanumeric code used to identify the programme or project.	Text	Once	HMTPROJ0001	HMG_S_68
Project features	GPD_1002_S_002	Project / Programme Name	A unique, brief title used to refer to the programme or project.	Text	Once	Project Gigabit	HMG_S_69
Project features	GPD_1002_S_003	Parent ID	The Project / Programme ID of the Parent Project or Parent Programme, if applicable.	Text	Once	HMTPROJ0001	HMG_S_204, HMG_S_205
Project features	GPD_1002_S_004	Child ID	The Project / Programme ID of the Child Project or Child Programme, if applicable.	Text	Once	HMTPROJ0001	HMG_S_202, HMG_S_203
Project features	GPD_1002_S_005	Lead organisation	The name of the primary government organisation delivering the project.	Plain text, Category	Once	Department for Environment, Food and Rural Affairs
Project features	GPD_1002_S_006	Project category	A categorical indication of the primary domain of the programme or project.	Plain text, Category	Once	Infrastructure and construction	HMG_S_71
Project features	GPD_1002_S_007	GMPP Status	A categorical indication of whether the programme or project belongs to the Government Major Project Portfolio.	Text	On change	Yes
Project features	GPD_1002_S_008	Project start date	The date the project begins. This date should be the beginning of the Feasibility Stage of the project and should follow the conclusion of the Policy Stage.	Date	Once	YYYY-MM-DD	HMG_S_28
Project features	GPD_1002_S_009	Project end date	The date on which the project will end. This date should be the end of the Operation Stage and precede Operations.	Date	Quarterly	YYYY-MM-DD	HMG_S_28
Project features	GPD_1002_S_010	Programme Director name	The name of the Programme Director.	Text	On change	Ben Salisbury
Project features	GPD_1002_S_011	Senior Responsible Owner name	The name of the Senior Responsible Owner.	Text	On change	Ben Salisbury
Risk	GPD_1002_S_012	Risk ID	Unique alphanumeric code used to identify the risk and its associated data.	Text	Once	PRJ1_RISK001
Risk	GPD_1002_S_013	Risk title	A brief summary to identify the risk.	Text	Once	Inclement weather
Risk	GPD_1002_S_014	Risk type	Indication of whether the risk is a threat or opportunity.	Plain text, Category	Once	Opportunity
Risk	GPD_1002_S_015	Risk cause description	A description of the events or situations that are not risks in themselves but act as sources and drivers for potential risks and can be internal or external to the portfolio, programme or project.	Text	On change	Caused by <event or situation>
Risk	GPD_1002_S_016	Risk cause category	A categorical indication of the area in which the risk cause may arise.	Plain text, Category	On change	Strategy
Risk	GPD_1002_S_017	Risk event description	A description of an occurrence or change of circumstances. This can be something that is expected that does not happen, or something unexpected that does happen. Events can have multiple causes and impacts and can affect multiple objectives	Text	Once	X may occur
Risk	GPD_1002_S_018	Risk event category	A categorical indication of the area in which the risk event could occur.	Plain text, Category	Once	Governance
Risk	GPD_1002_S_019	Risk impact description	A description of the effects of the risk on the objectives of the portfolio, programme, project or work package should the event occur.	Text	On change	…resulting in <impact on the objectives>
Risk	GPD_1002_S_020	Risk impact category	A categorical indication of the area that would be impacted by the risk event.	Plain text, Category	On change	Security
Risk	GPD_1002_S_021	Risk proximity	A categorical indication of how soon the risk is expected to occur from the date of assessment.	Plain text, Category	On change	Imminent
Risk	GPD_1002_S_022	Inherent risk rating	The result of the Inherent risk likelihood score multiplied by the Inherent risk impact score.	Numeric	Once	20
Risk	GPD_1002_S_023	Inherent risk likelihood score	An indication of the likelihood of this risk occurring (on a scale of 1-5, 5 being certain)	Numeric	Once	4
Risk	GPD_1002_S_024	Inherent risk impact score	An indication of the impact should this risk occur.	Numeric	Once	4
Risk	GPD_1002_S_025	Current risk rating	The result of the Inherent/ Current risk likelihood score multiplied by the Inherent/ Current risk impact score.	Numeric	Monthly	20
Risk	GPD_1002_S_026	Current risk likelihood score	A numerical indication of the likelihood of this risk occurring (on a scale of 1-5, 5 being certain).	Numeric	Monthly	4
Risk	GPD_1002_S_027	Current risk impact score	A numerical indication of the impact should this risk occur.	Numeric	Monthly	4
Risk	GPD_1002_S_028	Residual risk likelihood score	A numerical indication of the likelihood of the risk occurring after the risk response has been applied.	Numeric	On change	5
Risk	GPD_1002_S_029	Residual risk impact score	A numerical indication of the impact, should the risk occur after the risk response has been applied.	Numeric	On change	3
Risk	GPD_1002_S_030	Residual risk rating	The residual risk likelihood score multiplied by the estimated residual risk impact score following successful and complete implementation of selected risk response(s).	Numeric	On change	15
Risk	GPD_1002_S_031	Risk response category	Whether to avoid, treat, transfer, accept, share, exploit (etc) the risk.	Plain text, Category	On change	Exploit
Risk	GPD_1002_S_032	Risk response description	A description of the action required to manage the risk in line with the risk appetite.	Text	On change	To <risk response category> this risk, we will <description of actions>
Risk	GPD_1002_S_033	Risk response owner	Name of the individual responsible for implementing the selected risk response.	Text	On change	Ben Salisbury
Risk	GPD_1002_S_034	Risk response due date	The date by which the risk response should be carried out.	Date	On change	YYYY-MM-DD
Risk	GPD_1002_S_035	Risk owner	Name of the individual with the accountability and authority to manage the risk.	Text	Once	Ben Salisbury
Risk	GPD_1002_S_036	Raised by	Name of the person or body who identified the risk	Text	Once	Ben Salisbury
Issue	GPD_1002_S_037	Issue ID	Unique alphanumeric code used to identify the issue and its associated data.	Text	Once	PRJ1_ISS001
Issue	GPD_1002_S_038	Issue event description	Description of the issue at a level of detail where it can be managed effectively (such as at work package or project level).	Text	Once	X has occurred
Issue	GPD_1002_S_039	Issue cause	A description of the specific factors that caused the event to occur or the query/ concern/ change to be identified.	Text	Once	Caused by <event>
Issue	GPD_1002_S_040	Issue cause category	A categorical indication of the area in which the issue cause lies. For issues that are escalated from risks, the Issue cause category could relate to the risk cause category.	Plain text, Category	Once	Governance
Issue	GPD_1002_S_041	Issue effect	A description of the effects of the issue on the objectives of the portfolio, programme, project, or work package.	Text	Once	resulting in <effect>
Issue	GPD_1002_S_042	Issue impact category	A categorical indication of the type of impact the issue is having.	Plain text, Category	Once	Governance
Issue	GPD_1002_S_043	Issue identifier	The name of the person or body who has raised the issue.	Text	Once	Ben Salisbury
Issue	GPD_1002_S_044	Issue owner	Assignment of person/persons to management of event.	Text	On change	Ben Salisbury
Issue	GPD_1002_S_045	Issue response description	A description of the corrective action/response required to address the issue.	Text	Once	This issue will be addressed through <response>
Issue	GPD_1002_S_046	Issue status	A categorical indication of the status of the issue.	Plain text, Category	On change	Open
Issue	GPD_1002_S_047	Issue closure reason	Reason the issue was closed.	Text	Once	PRJ1_ISS001 was closed because <reason>
Benefit	GPD_1002_S_048	Benefits ID	Unique alphanumeric code used to identify the benefit and its associated data.	Text	Once	PRJ1_BEN001
Benefit	GPD_1002_S_049	Benefit title	A brief summary to identify the benefit.	Text	Once	Reduced Waiting Times for Public Services
Benefit	GPD_1002_S_050	Benefit description	A brief summary of the benefit including enabling programme, project or activity.	Text	Once	A digital booking system will reduce waiting times for council services by allowing citizens to schedule appointments online, improving access and efficiency.
Benefit	GPD_1002_S_051	Green Book benefit category	A categorical indication of the Green Book Benefit Category to which the benefit belongs. Benefit Categories indicate where the benefit is realised.	Plain text, Category	Once	Direct public sector
Benefit	GPD_1002_S_052	Green Book benefit class	A categorical indication of the Green Book Benefit Classification to which the benefit belongs. Benefit Classes indicate how the benefit is measured.	Plain text, Category	Once	Monetisable
Benefit	GPD_1002_S_053	Benefit owner	Name of the person responsible for the benefit.	Text	Once	Ben Salisbury
Benefit	GPD_1002_S_054	Related business case objective	The title of the related objective outlined in the relevant business case.	Text	On change	Improve citizen access to council services through digital transformation.
Benefit	GPD_1002_S_055	Related strategic objective	The title of the strategic objective to which the benefit relates.	Text	On change	PRJ1_BEN001 aligns with <objective>.
Benefit	GPD_1002_S_056	Full-year value of the benefit (forecast)	The forecast monetary figure of the full-year value of the benefit in £m.	Numeric	On change	1000
Benefit	GPD_1002_S_057	Full-year value of the benefit (actual)	The actual monetary figure of the full-year value of the benefit in £m.	Numeric	On change	1000
Benefit	GPD_1002_S_058	Realisation start date	The date on which the benefit will begin to be realised.	Date	On change	YYYY-MM-DD
Benefit	GPD_1002_S_059	Realisation end date	The date on which benefit realisation is complete.	Date	On change	YYYY-MM-DD
Benefit	GPD_1002_S_060	Benefit realisation time frame	The number of years over which the benefit will be realised. This is the difference between the Realisation start date and Realisation end date.	Numeric	On change	3.5
Benefit	GPD_1002_S_061	Beneficiary group	A categorical indication of the stakeholder group to whom the benefit will be of value.	Plain text, Category	On change	Government Department
Benefit	GPD_1002_S_062	Beneficiary	Stakeholder to whom the benefit will be of value.	Text	On change	HM Treasury
Milestone	GPD_1002_S_063	Milestone ID	Unique alphanumeric code used to identify the milestone.	Text	Once	HMT_PROJ0001_M001
Milestone	GPD_1002_S_064	Milestone title	A brief summary to identify the milestone.	Text	Once	Service Go Live
Milestone	GPD_1002_S_065	Milestone planned date (baseline)	Initial date on which the milestone is planned to complete. This is the baseline date and should not change.	Date	Once	YYYY-MM-DD
Milestone	GPD_1002_S_066	Milestone forecast date	The date on which the milestone is currently expected to complete. This should be the date currently in use internally within the project.	Date	On change	YYYY-MM-DD
Milestone	GPD_1002_S_067	Milestone actual date	The date on which the milestone was completed.	Date	Once	YYYY-MM-DD
Milestone	GPD_1002_S_068	Milestone category	Categorical indication of which area the milestone belongs to.	Plain text, Category	Once	Assurance
Milestone	GPD_1002_S_069	Milestone status	Categorisation of the delivery status of the milestone.	Plain text, Category	On change	On track
Milestone	GPD_1002_S_070	Milestone description	A description of the milestone that adds detail beyond the Milestone Title.	Text	Once	The service becomes live for all registered users.
Milestone	GPD_1002_S_071	Milestone critical status	Yes/No indication of whether the milestone is on the project’s critical path	Plain text, Category	On change	Yes
Milestone	GPD_1002_S_072	Milestone restricted status	Yes/No indication of whether the milestone should be treated as Official-Sensitive	Plain text, Category	On change	Yes
Milestone	GPD_1002_S_073	Milestone protected status	Yes/No indication of whether the information provided for this Milestone should be prioritised for protection during centralised reporting.	Plain text, Category	On change	Yes
Milestone	GPD_1002_S_074	Milestone comment	Text to support understanding of the milestone.	Text	On change	This milestone superseded two archived milestones: <milestone IDs>.
Cost	GPD_1002_S_076	Departmental baseline	The cost/benefit profile that was approved by the department nearest to the current reporting period. The approval can either come from a department-approved business case, or from the latest significant internal board. Departmentally approved / cost/benefit profiles should be reported in nominal terms. If your project doesnot have a cost/benefit profile that was approved by your department, return nil in this field. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_077	HMT approved estimate	The most recent cost/benefit profile that was approved by HMT. This means the / cost/benefit profile that was approved by HMT nearest to the current reporting period. The approval can come from an HMT desk-based review, a formal HMT approval, or a Major Project Review Group. HMT-approved cost/benefit profiles should be reported in nominal terms. If your project does not have a cost/benefit profile that was approved by HMT, return nil in this field. Input values in £m.	Numeric	On change	10000	CCoA project-related codes: / HMG_S_202 / HMG_S_203 / HMG_S_204 / HMG_S_205 / Finance project-related codes: / HMG_S_68 / HMG_S_69 / HMG_S_71
Cost	GPD_1002_S_078	Actual cost to date (Whole Life)	The incurred costs that are charged to the project account and for which payment has been made or accrued over the project to date. Input values in £m.	Numeric	On change	10000	CCoA project related codes: / HMG_S_202 / HMG_S_203 / HMG_S_204 / HMG_S_205 / Finance Project related codes: / HMG_S_68 / HMG_S_69 / HMG_S_71
Cost	GPD_1002_S_079	Forecast outturn (Whole Life)	The cost of actual expenditure, accruals and the estimate of the costs to complete the work to the end of the project. Input values in £m.	Numeric	On change	10000	CCoA project related codes: / HMG_S_202 / HMG_S_203 / HMG_S_204 / HMG_S_205 / Finance Project related codes: / HMG_S_68 / HMG_S_69 / HMG_S_71
Cost	GPD_1002_S_080	Variance (Whole Life)	Cost comparison between what has been funded and what has been spent over the course of the project so far. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_081	Actual cost to date (Financial Year)	The incurred costs that are charged to the project account and for which payment has been made or accrued over the Financial Year. Input values in £m.	Numeric	On change	10000	CCoA project related codes: / HMG_S_202 / HMG_S_203 / HMG_S_204 / HMG_S_205 / Finance Project related codes: / HMG_S_68 / HMG_S_69 / HMG_S_71
Cost	GPD_1002_S_082	Forecast outturn (Financial Year)	The cost of actual expenditure, accruals and the estimate of the costs to complete the work to the end of the Financial Year. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_083	Current budget (Financial Year)	The agreed cost of the project or a quantification of resources needed for the Financial Year to achieve an activity by a set time, within which the activity owners are required to work. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_084	Variance (Financial Year)	Cost comparison between what has been funded and what has been spent in the Financial Year. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_085	Actual cost (Month)	The incurred costs that are charged to the project account and for which payment has been made or accrued over the given month. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_086	Agreed funding for current stage	The monetary figure (funding) agreed for the current stage of the project. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_087	Agreed funding for next stage	The monetary figure (funding) agreed for the next stage of the project. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_088	One-off new costs (RDEL)	Monetary figure representing the investment in change - the “one off” project resource costs incurred by undertaking the project until its closure (not the Business case end date). They include the displacement costs associated with the project. Input values in £m.	Numeric	On change	10000	CCoA project related codes: / HMG_S_202 / HMG_S_203 / HMG_S_204 / HMG_S_205 / Finance Project related codes: / HMG_S_68 / HMG_S_69 / HMG_S_71
Cost	GPD_1002_S_089	One-off new costs (CDEL)	Monetary figure representing the investment in change - the “one off” project capital costs incurred by undertaking the project until its closure (not the Business case end date). They include the displacement costs associated with the project. Input values in £m.	Numeric	On change	10000	CCoA project related codes: / HMG_S_202 / HMG_S_203 / HMG_S_204 / HMG_S_205 / Finance Project related codes: / HMG_S_68 / HMG_S_69 / HMG_S_71
Cost	GPD_1002_S_090	Recurring new costs (RDEL)	Monetary figure representing ongoing resource expenditure that is needed to maintain/service etc. the asset implemented during the project. These costs may continue for some time after the project closure and may start before the project closes as the asset is being introduced into the business. Please only include costs that are included in the business case. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_091	Recurring new costs (CDEL)	Monetary figure representing ongoing capital expenditure that is needed to maintain/service etc. the asset implemented during the project. These costs may continue for some time after the project closure and may start before the project closes as the asset is being introduced into the business. Please only include costs that are included in the business case. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_092	Recurring old costs (RDEL)	Monetary figure representing resource expenditure which was ongoing prior to commencement of the project. The amount to be recorded relates to sums incurred only during the lifetime of the project if included in the Business Case figures upon which the investment decision was made. Not all projects will have old recurring costs and projects only need include the costs if they are included in the project Business Case. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_093	Recurring old costs (CDEL)	Monetary figure representing capital expenditure which was ongoing prior to commencement of the project. The amount to be recorded relates to sums incurred only during the lifetime of the project if included in the Business Case figures upon which the investment decision was made. Not all projects will have old recurring costs and projects only need include the costs if they are included in the project Business Case. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_094	Non-govt spend (RDEL)	Monetary figure representing resource expenditure met other than from the HMT (public finances). This may include contributions from suppliers, sums raised through levies etc. If a breakdown into RDEL and CDEL is available for the years for which information is requested on the return it should be provided. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_095	Non-govt spend (CDEL)	Monetary figure representing capital expenditure met other than from the HMT (public finances). This may include contributions from suppliers, sums raised through levies etc. If a breakdown into RDEL and CDEL is available for the years for which information is requested on the return it should be provided. Input values in £m.	Numeric	On change	10000
Cost	GPD_1002_S_096	Departmental baseline year	The financial year of the departmental baseline (i.e. Year zero – Y0). Dates should begin with 01/04.	Date	On change	YYYY-MM-DD	HMG_S_28
People	GPD_1002_S_097	Current Headcount	The total number of employees employed by the project.	Numeric	On change	25	HMG_S_229 / HMG_S_583
People	GPD_1002_S_098	Total approved FTE	The total number of approved positions for the project, as determined by organisational headcount controls.	Numeric	On change	27	HMG_S_229
People	GPD_1002_S_099	Total funded public sector employees (FTE)	The total number of full-time equivalent civil servants/crown personnel approved for the project team (as agreed in the most recent, relevant business case).	Numeric	On change	100.5	HMG_S_40 / HMG_S_583 / HMG_S_12 / HMG_S_219
People	GPD_1002_S_100	Total public sector employees in post (FTE)	The total number of full-time equivalent civil servants/crown personnel currently in-post in the project.	Numeric	On change	100.5	HMG_S_40 / HMG_S_583 / HMG_S_12 / HMG_S_219
People	GPD_1002_S_101	Total current vacant posts carried (FTE)	The total number of approved full-time equivalent positions that are yet to be filled, including civil servants, crown personnel, contracted, and contingent employees.	Numeric	On change	2	HMG_S_40 / HMG_S_12
People	GPD_1002_S_102	Total vacant posts carried (next 12 months) (FTE)	The total number of approved full-time equivalent positions that are unfilled but are planned to be filled within the next 12 months, including civil servants, crown personnel, contracted, and contingent employees.	Numeric	On change	4	HMG_S_40 / HMG_S_12
People	GPD_1002_S_103	Total project delivery posts (FTE)	The total number of full-time equivalent posts in the project team which align with the project delivery profession, either named within the Project Delivery Capability Framework or other project delivery-specific roles.	Numeric	On change	15	HMG_S_229 / HMG_S_583 / HMG_S_12 / HMG_S_219
People	GPD_1002_S_104	Current contracted and contingent employees (FTE)	The total number of full-time equivalent contracted and contingent employees currently in-post in the project team.	Numeric	On change	5	HMG_S_40 / HMG_S_219 / HMG_S_219
Metadata	GPD_1002_M_001	Date created	The date on which the data was created.	Date	Once	YYYY-MM-DD
Metadata	GPD_1002_M_002	Last modified	The most recent date on which the data was updated.	Datetime	On change	YYYY-MM-DD hh:mm:ss
Metadata	GPD_1002_M_003	Closure date	The date on which the entry was closed.	Date	Once	YYYY-MM-DD
Metadata	GPD_1002_M_004	Created by	The name of the person who created the data.	Text	Once	Ben Salisbury
Metadata	GPD_1002_M_005	Modified by	The name of the person who modified the data.	Text	On change	Ben Salisbury