To: 	[Name of SRO], Senior Responsible Owner for the [Name] [Project/Programme]

From: 	[Name], [Job title of Accounting Officer] of [Department]

| [Insert Date] | Departmental Major Project (DMP) |
| --- | --- |

Dear [Name],

## Appointment as senior responsible owner for the [name] [project/programme]

I am writing to confirm your appointment as Senior Responsible Owner (SRO) of the [project/programme name] with effect from [date of appointment]. This letter sets out your responsibilities and the support you can expect from the department.

As SRO, you are directly accountable to [name of business owner, for example, the sponsoring Director General or chief executive of an Arm’s Length Body], under the oversight of the [job title] as accounting officer for [department], and [name and title of responsible Minister].

Your [project/programme] forms part of the [departmental portfolio name] and is included in the Departmental Major Projects Portfolio (DMP).

You have personal responsibility for the delivery of [project/programme or specific tranches, stages etc. if relevant] and will be held accountable for the delivery of its objectives, policy intent and outcomes. This encompasses securing and protecting its vision, ensuring that it is governed responsibly, reported on honestly, escalated appropriately and for influencing the context, culture, and operating environment of the [project/programme]. You are also responsible for ensuring the ongoing viability of the [project/programme] and recommending its pause or termination if appropriate. Where issues arise that you are unable to resolve, you are responsible for escalating these to [name of governance body].

In addition to your internal accountabilities, SROs for DMP projects and programmes are personally accountable to Parliamentary Select Committees. This means that, from the date of this letter, you will be held personally accountable to and could be called by Select Committees to account for and explain the decisions and actions you have taken to deliver the [project/programme or specific milestone/deliverable].

You are expected to run your project/programme in accordance with the Government Functional Standard for Project Delivery, and the requirements of other functional standards as required, which are mandated for government departments and arm’s length bodies. You should also make yourself familiar with The Teal Book, Government Project Delivery’s code of practice for project delivery, and any further guidance and requirements set by [departmental portfolio office, Centre of Expertise etc.].

### Time commitment and tenure

[This will be a full-time role to enable effective delivery of the role and execute your responsibilities in full.

OR

This role will require [at least 50%] of your time to enable effective delivery of the role and execute your responsibilities in full.]

You are required to undertake this role until achievement of [agreed delivery milestone, which could be project/programme close, or the end of a specific phase of the project], planned for [date]. Progress towards this will be reflected in your personal objectives.

### Objectives and performance criteria

The policy intent supported by this [project/programme] is [explain policy intent, including where this contributes to enabling a transition to Net Zero GHG emissions by 2050].

Any proposed changes to scope which impacts on this intent or the realisation of benefits must be authorised by [management board] and may be subject to further levels of approval.

The vision of the [project/programme] is [describe the vision] and its objectives are to:

- [list objective(s)]

Your personal objectives and performance criteria which relate to the [project/programme] are:

[list performance objective(s), including natural environment, adaptation & Net Zero objectives, e.g. to reduce GHG emissions from [infrastructure topology/activity etc.] by [% or actual kg/Mt CO2e] by [time].]

### Extent and limit of accountability

#### Finance and Controls

HM Treasury spending controls apply, on the basis set out within the Department’s delegated authority letter. Where the [project/programme] exceeds the delegated authority set by HM Treasury, the Treasury Approval Point (TAP) process will apply, and the details of each approval process must be agreed with your HM Treasury spending team. You should consult Departmental finance colleagues on how to go about this.

You should note that where expenditure is considered novel, contentious, repercussive, or likely to result in costs to other parts of the public sector, HM Treasury approval will be required, regardless of whether the programme expenditure exceeds the delegated authority set by HM Treasury. If in doubt about whether approval is required you should, in the first instance, consult Departmental finance colleagues before raising with the relevant HM Treasury spending team.

The overall estimated budget, resourcing requirements and tolerances for your project/programme will be agreed as part of the approval process.

You should operate at all times within the rules set out in Managing Public Money. In addition, you must be mindful of, and act in accordance with, the Department’s specific HM Treasury delegated limits and with the wider approach to functional controls set out in the Department’s Memorandum of Understanding with the Treasury.

#### Delegated authority

[You are authorised to:

- approve expenditure of [£nn];

- agree project rescheduling within [insert tolerance period] of agreed milestones, but rescheduling beyond that must be agreed with [business owner or appropriate governance body]; and

- recommend to [business owner] and the [appropriate governance body] the need to either pause or terminate the programme where necessary and in a timely manner.]

These authority limits are subject to change and other conditions or tolerances may be set as part of the business case approval and ongoing monitoring processes within which you should then operate.

Where issues arise which take you outside of these authority limits which you are unable to resolve, you are responsible for escalating these issues to the [business owner] and the [appropriate governance body].

#### Appointments

You should appoint a full time [project/programme] director to support you in the management of this [project/programme] and make other appointments as required for the control and delivery of your programme within your delegated authority.

#### Governance and assurance

You should pay attention to ensuring effective governance for your [project/programme], including the establishment of a [project/programme] board with appropriate membership and clear terms of reference.

As primary owner, you must ensure that the [project/programme] secures business case approval from [insert management board(s)]. You should also ensure that the [project/programme] remains aligned to the strategic outcomes, costs, timescales, and benefits in line with the approved business case as well as monitoring the context within which the [project/programme] is being delivered to ensure it remains valid.

Where a change impacts the scope, costs, benefits, or planned delivery milestones agreed as part of an agreed business case, you are responsible for following the agreed change request approval process and setting a new, approved, business case baseline.

You should ensure that approval of the Outline Business Case includes appropriate assessment from the perspective of the Accounting Officer. Whilst published accounting officer assessments are not required for projects and programmes outside the GMPP, the guidance for major projects offers a useful framework. Similarly, you are responsible for bringing to the attention of the Accounting Officer any material changes in the [project/programme] which could require a new assessment. Guidance on completing accounting officer assessments for major projects is available from HM Treasury.

Your Accounting Officer will wish to consider how any assessments published previously should be treated, if your project or programme fell within the GMPP in the past. In such cases e.g. the Accounting Officer may wish to publish any updated assessments – even where publication is not required – or to annotate the relevant landing page, so that external readers can see the up-to-date position.

[You are responsible for providing assurance to the Accounting Officer and relevant oversight bodies that the Environmental Principles Policy Statement legal duty has been considered by Ministers in policy decision underpinning the project/programme.]

Although you are directly accountable for this [project/programme], you are also expected to support delivery of the department’s overall strategic objectives. This means that you are expected to work collaboratively with other SROs and project directors in adjacent projects and programmes and with the [portfolio name] portfolio management office and portfolio director to manage dependencies, resources, schedules, and funding to support delivery of the overall change the department needs to achieve its strategic objectives.

You should ensure that appropriate and proportionate assurance is in place and agree on the level and frequency of assurance reviews through the maintenance of an Integrated Assurance and Approvals Plan. You should develop this plan and its maintenance in collaboration with the Departmental Assurance Coordinator.

[For DMP SROs: You are responsible for ensuring the honest and timely reporting on the position of the [project/programme] to the National Infrastructure and Service Transformation Authority (NISTA) and for providing reports and information to the [departmental portfolio name] portfolio management office as required.

[As the SRO for a project/programme that is within scope of the Clean Energy Superpower Mission (CESM), you are additionally required to report, via relevant net zero portfolio / sector Boards and the Net Zero Directors governance forum, into the CESM governance structure as part of the Accelerating to Net Zero pillar of the Mission.]

Whilst the business cases of programmes and projects falling outside the GMPP need not be deposited in the House of Commons Library – and so that is not needed for [project / programme] – your Accounting Officer will wish to consider how to treat any projects or programmes that fell within the GMPP in the past. In such cases e.g., the accounting officer may suggest Ministers deposit a note in the Library, so that any external readers can see the up-to-date position.

#### Evaluation

Evaluation is a requirement for all programmes and projects needing approval through HM Treasury’s Approvals Process. As an SRO of such a [project/programme], you are accountable for ensuring that your [project/programme] has a robust, proportionate and suitably resourced evaluation in place. Evaluation planning should begin from the very start of the policy development and the initiation of the [programme/project]. Progress with the development and implementation of evaluation plans will be monitored through the major project assurance process.

You are also required to register all planned, live and completed evaluations on the Government Evaluation Registry. Guidance on using the evaluation registry is available on GOV.UK.

### Development and support

[As a graduate of the Major Projects Leadership Academy, you are expected to maintain your continuing professional development as a project leader,

OR

[As SRO of a DMP [project/programme], you are eligible to apply for the Major Projects Leadership Academy.

To widen experience and understanding of the role, SROs are also expected to lead or participate in such reviews for other government departments, the wider public sector, and other areas of the [department name] as appropriate. Becoming an assurance reviewer and completing a review will form part of your time at the Major Projects Leadership Academy.

The Department will assist you in securing the necessary resources to support the [project/programme], and will set clear guidance, requirements and standards, which align to the Government Functional Standard on Project Delivery, to enable good governance and effective delivery. You will be part of the Department’s cohort of major project leaders who will be expected to support each other, share good practice and lessons learned and to collectively develop solutions. You should liaise with the Department’s Head of Profession for project delivery to discuss the maintenance and development of your delivery and leadership skills.

Following approval of the business case and entry onto the [name of departmental portfolio], the [portfolio governance body] will provide ongoing oversight and support and will take steps to help resolve and escalate risks, issues or constraints that are acting as a blocker to successful delivery.

I wish you every success in your role as SRO.

Yours sincerely,

| [NAME] |  |  |
| --- | --- | --- |
| [Job title of the Accounting Officer] [Department] |  |  |

CONFIRMATION OF ACCEPTANCE OF APPOINTMENT

I confirm that I accept the appointment of Senior Responsible Owner for the [project/programme], including my personal accountability for implementation, as set out in the letter above.

[NAME OF SRO]

[Date]